**NOTICE TO BUSINESSES**

**MARCH 29, 2019**

**Clinton Avenue**

**3rd Street to Riverside Avenue**

Beginning this week of April 8th, the contractor will begin preparations for the reconstruction of Clinton Avenue from 3rd Street to Riverside. It is anticipated that this project will take 7 weeks to complete. Work will include the reconstruction of the road as well as the replacement of the storm sewers.

The contractor’s current schedule is as follows:

Mobilization and Set up Traffic Control April 8th

Stage 1 (Westbound Lanes) Removals and Storm Sewers April 9th – April 14th

Stage 1 Earth excavation, Underdrains and Stone Base April 15th – April 17th

Stage 1 Paving and Cure April 18th – April 25th

Stage 1 Drive Approaches/sidewalks April 26th – April 30th

Stage 1 Restoration May 1st – May 2nd

Open Stage 1 to traffic and Close Stage 2 May 3rd

Stage 2 (Eastbound Lanes) Removals and Storm Sewers May 4th – May 6th

Stage 2 Earth excavation, Underdrains and Stone Base May 7th – May 9th

Stage 2 Paving and Cure May 10th – May 16th

Stage 2 Pave Gap and approach to Pepper Joes May 17th – May 21st

Stage 2 Restoration May 22nd - May 23rd

Pavement Marking and Permanent Signage May 24th

Final Cleanup and Restoration May 25th – June 1st

During Stage 1, eastbound traffic will be maintained on Clinton Ave and westbound traffic will be detoured north on Riverside to Vine Street, west on Vine Street to 6th Street and south on 6th Street to Clinton Ave. Access to Tim Hortons and Burger King will be off Riverside and access to Talmer Bank will be off 3rd Street during Stage 1 construction.

During Stage 2, westbound traffic will be maintained on Clinton Avenue and eastbound traffic will be detoured north on 6th Street to Vine Street, east on Vine Street to Riverside and south on Riverside back to Clinton Ave. Access to Pepper Joes will be maintained off of Clinton Ave.

**There will be no interruption of emergency services at any time during construction.**

Regular work hours during construction will be 7:00 a.m. to 5:00 p.m., Monday through Friday.

The City of St. Clair wishes to apologize in advance of the impending construction for any inconvenience it may cause you and hopes, with your cooperation, to complete the construction in a timely manner.

If you have any questions or concerns, please feel free to contact any of the following:

Contractor: M.L. Chartier Excavating, Inc. (586) 725-8373

Engineer: Anderson, Eckstein and Westrick, Inc

Stephen Pangori (586) 855-9551 - cell

(586) 726-1234 - office

Thank You.